## Status Report
Project Name | Hot Dog Not Dog |  | Date |  | 2020-01-24 | Project Manager |  | Chase Wheeler
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
This would be an app that allows a user to take a picture of something, and then will tell the user if what they have is a hot dog or not a hot dog. |  |  |  | Organization Chart |  | 100% | Complete
|  |  |  | System Architecture Design |  | 25% | On Track
|  |  |  | Requirements |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Organization Chart | [5 empty] | Requirements
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Chase Wheeler | PM/FED | 5 | Risk | Not enough time to train neural network The ambiguity of running a neural network on an app
Michael Briggs | CA/FED | 5
Jeffery DeGraw | QA/BED | 5
Aaron Anthony | BED | 5 | Issue | .
Total |  | 20

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task